## Slide 1
Authorize 90 days to make the next treasury decision
Federated coordination · local-stabilization fallback · no production or funding authorization
Notes: Decision requested: authorize evidence mobilization, named owners, G0–G6 gates, and the explicit fallback. Day 90 returns for a separate stop / extend / bounded-pilot decision. Nothing in this deck authorizes production change, cash movement, account closure, labor action, procurement, spend, benefit recognition, or scale. Classification: Confidential — simulated client material.

## Slide 2
ACG has enough evidence to choose a direction—not enough to approve value or production
The first commitment is ownership and controlled evidence
58.18%
same-day proxy visibility · 5,792 / 9,955 account-days
6.30%
payment exceptions · 479 / 7,600 supplied records
87
federated option score · vs 72 local / 60 global
$0
recognized value today · cash, P&L, capacity
Sources: W2 visibility/payment diagnostics; W3 option/value models
2/18
Notes: This is the conclusion loop. The diagnostic numbers create urgency and direction but not investment authority. Visibility is a calendar-date proxy. Payment metrics are within the supplied extract. The option score is analyst judgment. Zero recognized value is an evidence-control status, not a claim of zero opportunity or risk.

## Slide 3
Four linked failures explain ACG's treasury problem
The recommendation must fix ownership, evidence, control, and service together
Failure | Evidence | Management implication
Visibility | 58.18%; 2,534 ≥2d | Own source, cutoff, reconciliation, exception
Liquidity | $21m/$35m/$46.2m | Certify mobility, buffers, economics before action
Payment operation | 31.51% manual touch; 6.30% exceptions | Prove causes; standardize safely
Operating model | Local practices; three ERPs; no enterprise TMS | Federated policy/data/control spine with local rights
READOUT
Visibility: 58.18%; 2,534 ≥2d
Liquidity: $21m/$35m/$46.2m
Sources: W2 diagnostic report; W3 future-state operating model
3/18
Notes: The four failures form the system map for the rest of the deck. The slide does not claim that technology is unimportant; it places integration behind a governed operating model. Stakeholder statements are corroborating context, not proof.

## Slide 4
Portal and spreadsheet sources explain every delayed account-day in the supplied pattern
Automated sources are same-day under the proxy; manual sources are not
Chart: 
| API | Host-to-host | Portal | Spreadsheet
Same-day account-days (%) | 100 | 100 | 0 | 0
READOUT
23 manual sources · 58.18% proxy · calendar-date only
Sources: W2_visibility_diagnostic.csv · Jan–Jun 2026
4/18
Notes: The source-method concentration makes the first intervention testable: controlled source, receipt timestamp, balance type, owner, and exception. It does not prove that the method itself is causal; method can proxy for entity, bank, process, or data ownership.

## Slide 5
The liquidity analysis defines a certification agenda—not a cash-release claim
14-day screen pass rates fall from 100% to 0% as the threshold rises
Chart: 
| $21m downside | $35m base | $46.2m upper
Complete windows meeting threshold (%) | 100 | 82.14 | 0
READOUT
168 windows · $0 recognized cash · VG01–VG05 open
Sources: W2_liquidity_thresholds.csv; W3 business case
5/18
Notes: The base $35m screen passes 138 of 168 complete windows. The slide avoids the word available. An account enters a funding decision only after current source, restriction, buffer, local/service context, timing, economics, authority, and Finance evidence close.

## Slide 6
Payment friction is material enough to diagnose—and too weakly evidenced to automate broadly
Within the supplied 7,600-record extract
31.51%
manual-touch rate · 2,395 records
6.30%
exception rate · 479 records
5.00%
late-release rate · 380 records
10.34%
cross-border · 786 records
Sources: W2_payment_diagnostic.csv; W3 payment pilot charter
6/18
Notes: Manual-touch records have higher exception and late-release rates than non-manual records, but association is not causality. The 120-record frame contains four mutually exclusive cohorts and is designed for root-cause evidence, not prevalence, enterprise extrapolation, or a benefit claim.

## Slide 7
The root causes sit upstream of the visible symptoms
Each root cause requires an owner and an observable control
01
Ownership is split
Data · mobility · value
02
Data is incomplete
Lineage · timestamps · populations
Process & service
Variable intake, cutoffs, repair loops and emergency practice.
Control & technology
Access · SoD · audit · resilience tests
Do not automate an undefined process or centralize an uncertified decision right.
Sources: W2 process/RACI and maturity heatmap; stakeholder pack
7/18
Notes: The maturity implication is qualitative: the operating model is fragmented across the four root-cause domains. The deck does not claim technology is causal. It assigns technology as an enabler after ownership, source, process, service, and control rules are explicit.

## Slide 8
Eight design principles resolve the tension between enterprise control and local responsiveness
Critical gates remain non-compensating
Enterprise spine
Daily evidence · global ownership · common policy · controlled metrics
Local rights
Certified context · local rights · visible exceptions
Control by design
SoD · access · audit · reconciliation · service · resilience · rollback
Staged and reversible
Existing ERPs · bounded cohorts · gates · rollback · local fallback
Any failed critical gate blocks the affected decision; value cannot compensate.
Sources: W3 design principles and operating model
8/18
Notes: The full eight principles are client service, daily evidence, federated decision rights, standardization with exceptions, control, resilient staged integration, data ownership, and scalable acquisition readiness. This slide groups them into four board-level design choices.

## Slide 9
Federated coordination offers the best balance with a local fallback
Weighted option score / 100; scores select direction, not execution readiness
Chart: 
| Federated | Local | Global
Weighted score | 87 | 72 | 60
READOUT
5/5 sensitivity wins · 0 gates closed · switch on failure
Sources: W3_option_summary.csv; W3_option_sensitivity.csv
9/18
Notes: The option criteria and weights were locked before scoring. Scores are analyst judgment and do not include diagnostic benefit quantities. Global coordination remains on hold until legal/local, architecture, cyber/resilience, service, cost, mobility, and rollback evidence materially closes.

## Slide 10
The target model centralizes standards and evidence—not every operational decision
One enterprise spine with governed regional and local execution
Global spine
• Treasury: policy, data, position and mobility standards
• CIO: integration, access, audit, cyber and resilience
• Finance: cost/benefit admission and change control
Regional and local rights
• Regions/BU: context, requests, critical service and emergencies
• Shared Services: payment execution and exceptions
Internal Audit remains independent; Legal/Tax owns specialist conclusions; every production pilot requires a separate go/no-go.
Sources: W3 future-state process/RACI; final governance/RACI
10/18
Notes: The model addresses local concerns by making context and emergency rights explicit instead of informal. One accountable owner remains required per activity. Global policy ownership does not transfer every execution step to headquarters.

## Slide 11
Seven initiatives start with data, governance, and value control—not platform procurement
Priority score combines value 30%, risk 25%, feasibility 20%, dependency 15%, speed 10%
Rank | Initiative | Score | Accountable owner | First exit
1 | Cash data & visibility | 94 | Group Treasurer | G1 metric/population contract
2 | Benefits, cost & KPI assurance | 92 | CFO / Finance Benefits | G2 cost evidence
3 | Governance, service & adoption | 86 | CFO / Treasurer | G1 RACI and rights
4 | Payment controls & exceptions | 85 | Shared Services | Day 75 cause readout
5 | Liquidity certification | 83 | Group Treasurer | G2 certification design
6 | Integration, access & resilience | 80 | CIO | G3 rollback pass
7 | Account rationalization | 63 | Group Treasurer | Per-account G2 decision
READOUT
1: Cash data & visibility
2: Benefits, cost & KPI assurance
Sources: W4_initiative_portfolio.csv · model v1
11/18
Notes: I01, I07 and I06 start together because controlled data, value governance and decision rights are dependencies for all other work. Account rationalization ranks last because its direct fee case is modest, although it can progress quickly and safely with per-account validation.

## Slide 12
The business case stays credible by keeping unlike value types separate
Current validated, funded, and recognized value remains zero
Value type | Diagnostic quantity | Recognized | Admission gate
Cash release | $21m / $35m / $46.2m screens | $0 | VG01–VG05
Annual P&L | $3,900 / $7,800 / $7,800 fee sensitivity | $0 | VG06–VG07
Productive capacity | 50 / 150 / 150 hours/month | $0 | VG08–VG10
Risk reduction | Exposure and value not quantified | $0 ledger entry | VG11–VG12
READOUT
Cash release: $21m / $35m / $46.2m screens
Annual P&L: $3,900 / $7,800 / $7,800 fee sensitivity
Sources: W3 business-case/value/cost outputs; W4 benefits tracker
12/18
Notes: The base one-time planning amount fits the $1.0–$1.5m disclosed ceiling; the high case exceeds it by $215k. The base recurring amount is $281k per year and needs separate budget approval. ROI, NPV and payback remain unavailable because recognized benefits and actual cost/timing inputs are absent.

## Slide 13
Use 90 days to earn a bounded test before scaling
Day 90 is a decision gate—not a launch date
0–30D
Own the facts
Lock populations, sources, owners and baselines.
31–60D
Prove conditions
Close local, control, architecture and cost gaps.
61–90D
Make ready
Prepare cohort gates, controls, rollback and freeze path.
M4–6
Wave 1
Separate approvals; bounded visibility and safe change.
M7–12
Wave 2
Scale only where cash and payment evidence holds.
Sources: W4 roadmap/stage-gate outputs; NA freeze constraint
13/18
Notes: The sequence is dependency-led. Any delay in critical evidence moves later dates right without weakening the gate. North America production routing or approval-workflow change cannot occur in the confirmed eight-week Q4 freeze and requires Rachel Kim's sign-off; exact dates remain open. Month 5 is the earliest realistic NA production planning floor.

## Slide 14
Governance converts the roadmap into stop, switch, and scale decisions
Critical risk cannot be averaged away
Risk / trigger | Preventive control | Decision owner | Response
Unowned metric | G1 contract | CFO / Treasurer / CIO | Narrow, extend with owner/date, or switch
Uncertified cash | VG01–VG05; $0 eligible | Treasurer / Finance | No action; keep value at $0
Service / control / rollback failure | Blackout, emergency rights, tests | BU Finance / CIO / Control | Stop and rollback
Cost > $1.5m or run budget absent | CR01–CR10; separate budgets | CFO / SteerCo | Stage, redesign, or switch
Value formula or population drift | Finance dictionary/change control | Finance Benefits | Suspend, restate, review
DECISION
Unowned metric: G1 contract
Uncertified cash: VG01–VG05; $0 eligible
Sources: W4 risk register; final governance/RACI
14/18
Notes: The governance system separates workstream management from gate authority. Finance Benefits admits value. Management control owners approve control design. Internal Audit remains independent. A program cannot remain indefinitely amber: G2 and G3 require an explicit decision.

## Slide 15
Approve the direction and owners; return at Day 90
Five Steering Committee commitments activate the mobilization
DAY 0
Confirm direction
CFO/SteerCo · signed fallback and boundary
DAY 30
Accept owners
Executives · RACI and source/metric contracts
DAY 30
Lock NA calendar
Rachel Kim/CFO · freeze dates and sign-off path
DAY 60
Prove affordability
Finance/CIO/Procurement · CR01–CR10 pack
DAY 90
Take G3 decision
CFO/SteerCo · stop, extend or bounded pilot
Sources: Final recommendation memo; W4 decision log
15/18
Notes: Close with the same answer as slide 1, now supported by evidence. The decision should state what is approved, what is not approved, the owners, conditions, fallback, and date of the next decision.

## Slide 16
Appendix — Definitions, data quality, and methods bound every metric
Analysis | Method / definition | Data quality | Boundary
Visibility | Same-date days ÷ expected days | 9,955 rows; all delays use Portal/Spreadsheet | Proxy—not start-of-day/24h
Liquidity | 14-day minimum regional net | 168 windows; no mobility fields | Screen—not movable cash
Payments | Flags ÷ 7,600 records | Extract; no certified denominator | Association—not cause
Accounts | Dormant + legacy + zero payments | 55 accounts; local links untested | Candidate—not closure
Capacity | Frequency × time × manual % | Management estimates; repairs unreconciled | Hours—not headcount/P&L
READOUT
Visibility: Same-date days ÷ expected days
Liquidity: 14-day minimum regional net
Sources: W1 data-quality report · W2 metric contract and processed outputs
16/18
Notes: This appendix combines the required definitions, data-quality limitations, and methods. Full formulas, exclusions, source paths, alternative definitions, and tests are in the Week 2 metric contract and analysis logs.

## Slide 17
Appendix — Detailed analyses, sensitivities, and rejected alternatives support the choice
Analysis | Base result | Sensitivity / rejected alternative | Decision implication
Operating model | Federated 87 vs local 72 vs global 60 | Wins 5/5 weights; reject global-now/local-only | Federated now; local fallback
Liquidity | $35m base screen passes 138/168 windows | $21m: 168/168; $46.2m: 0/168 | Certify before action
Accounts | 4 candidates; $7,800/year estimated fees | 2 / 4 / 4 candidates across diagnostic cases | Validate one by one; no bulk closure
Capacity | 150 productive hours/month hypothesis | 50 / 150 / 150 h/month; 617.72 total estimate | Hours are not headcount/P&L
Affordability | $1.155m one-time + $281k/year recurring base | $755k / $1.155m / $1.715m; high +$215k | Source at G2; stage/redesign/switch
READOUT
Operating model: Federated 87 vs local 72 vs global 60
Liquidity: $35m base screen passes 138/168 windows
Sources: W2 diagnostic outputs · W3 option, sensitivity, business-case and cost outputs
17/18
Notes: This is the compact detailed-analysis and sensitivity appendix. Rejected alternatives are explicit: immediate global coordination, indefinite local-only remediation, bulk account closure, automatic payment automation, and premature labor or benefit claims.

## Slide 18
Appendix — Source and assumption controls keep claims auditable
01
PROGRAM + ACG
PROGRAM-STANDARD · ACG-DATA
02
CALCULATED
Reproducible ANALYST-CALC
03
OPEN INPUTS
ANALYST-ASSUMPTION · JUDGMENT
04
CONTEXT + AUDIT
JPM-PUBLIC · full register
Labels and paths: W4 source + assumptions registers · final evidence register · rebuild via src/ + data/processed/
Sources: W4 source and assumptions registers · Final evidence register · 24 Aug 2026
18/18
Notes: The source register and assumptions register are part of the final evidence pack. Public material is context only. The rebuild chain runs from source datasets through documented Python outputs and fail-closed tests to the deck, memo, roadmap, KPI dictionary, and benefits dashboard.